## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Read specs and get API access | 0.75 | 2023-10-06 | Understand what is expected and how the API is structured
CRUD setup and view results | 1.5 | 2023-10-09 | Setup the apiService.js to have access to the different endpoints
Basic styling of pages and content | 3 | 2023-10-09 | Getting everything in place and reference the styling guide, added about page | *
Router setup and detail page styling | 3 | 2023-10-09 | Needed the router functionality for the house detail pages, first styling of page
Create inputs and forms | 1 | 2023-10-10 | Creating the forms, getting all the inputs placed for the create page
Styling nav and sorting buttons | 2 | 2023-10-10 | Styling and functionality of nav and sorting buttons
Form styling | 2 | 2023-10-10 | Making the form look as it should
Upload and Create form functionality | 1 | 2023-10-10 | Making the forms work properly especially the image upload functionality
Form validation | 1 | 2023-10-11 | Initial form validation and styling
Delete functionality | 1 | 2023-10-11 | Set up the initial delete functionality
Delete and Edit icons placement & Modal | 3 | 2023-10-11 | Combine that functionality in the modal and link it with the icons
Forms & validation refactor | 2 | 2023-10-12 | Felt there was tow much repeat code so used one form for both create and edit
Search functionality | 1 | 2023-10-12 | Created the search functionality and results count
Vuex store setup | 1 | 2023-10-12 | Setup up the Vuex store to store the house from the API and use for main page
Mobile friendly styling | 4 | 2023-10-12 | Went through and made both styling changes and conditional component rendering
Mobile friendly styling | 2 | 2023-10-13 | More of the same, finishing the last bits
Cleanup and comments | 1 | 2023-10-13 | Went through the files and checked for any unused code or css, add comments
Total amount of hours | 30.25